## Hoja1
Path | Document | In Document |  |  | Category | Estimated Additional Workload | 3rd Parties | Comment
|  | Page # | Chapter | Section
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap03-SeleccionIntegrador_150413 | 5 | 3 | 1 | Missing Section | High | IPT-FV | Requires Chapter 11
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap03-SeleccionIntegrador_150413 | 5 | 3 | 1 | Missing Addendum/Appendix/Annex | High | IPT-FV | (i) Invitation Letter (ii) Integrator Survey (iii) Demo Summons
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap03-SeleccionIntegrador_150413 | 7 | 3 | 3 | Missing Section | High | IPT-FV | Dev Lifetime ~ Project Lifetime
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap05-GruposUsuarios_150423 | - | 5 | - | Missing Information | High | IPT-FV | Missing user group workflows
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap05-GruposUsuarios_150423 | - | 5 | - | Missing Information | Medium | IPT-FV | Missing user group job description: (i) Regional Manager (ii) HQ Manager (iii) PRL (iv) RR.HH (v) Planificación Producción (vi) Management Financiero
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap05-GruposUsuarios_150423 | 18 to 23 | 5 | 13 to 16 | Missing Information | Medium | IPT-FV | Missing user group definition: (i) Marketing (ii) Administrador IT (iii) CRM Data Entry Assistant (iv) Key Users
~/DRE/_DRE_CapitulosPorFirmar | IPT_ACRM_DRE_Cap08-BBDD_150413 | - | 8 | - | Outdated Chapter | High | - | Current version is very outdated.
~/DRE/cap06-Workflows | 20150408 Workflows | - | - | - | Unfinished Excel | Medium | IPT-FV | Workflows excel sheet
~/DRE/cap06-Workflows/VTA | IPT_ACRM_PRO_ProcesoVentas_150423 | 5, 14-19 | 2 | 1,4,5 | Outdated Section | High | - | (i) VTA.010- Establecimiento de costes (ii) VTA.040 - Proyectos
~/DRE/cap06-Workflows/VTA | IPT_ACRM_PRO_ProcesoVentas_150423 | 9 | 2 | 2 | Missing Information | Medium | IPT-FV | "Documentos", "Dependencias y Limitaciones"
~/DRE/cap08-BasesDeDatos | - | - | - | - | Formatting Fix | Low | - | (i) In Long / List field put source field in brackets (ii) BD ## -> BD##
~/DRE/cap08-BasesDeDatos | IPT_ACRM_BD1_companies_150421 | - | - | - | Missing Fields | Medium | IPT-FV | (i) Newsletter (ii) TPP (i) OPP
~/DRE/cap08-BasesDeDatos | IPT_ACRM_BD2_contacts_150401 | - | - | - | Missing Fields | Low | IPT-FV | Newsletter
~/DRE/cap08-BasesDeDatos | IPT_ACRM_BD3-ArticulosProductos_150422 | - | - | - | Missing Fields | Low | IPT-FV | Newsletter
~/DRE/cap08-BasesDeDatos | IPT_ACRM_BD9_Claims_borrador | - | - | - | Unfinished Excel | Medium | IPT-FV | BD9 Claims - Draft version